## Master Gantt
Blockmediary — Master Governance Gantt
Reporting period 8 June–14 August 2026 ¦ Status date 12 August 2026 ¦ Pre-remediation snapshot ¦ Individual-assignment work excluded
DONE | [11 empty] | REVIEW | [11 empty] | DOING | [11 empty] | TO DO | [11 empty] | DEFERRED | [11 empty] | ACTIVE COMPLETE
24 | [11 empty] | 8 | [11 empty] | 6 | [11 empty] | 6 | [11 empty] | 8 | [11 empty] | 54.55%
◆ Milestone column ¦ ◆ Zero float ¦ ● Critical path ¦ Gantt finish uses current due for active work, otherwise baseline finish | [11 empty] | ◆ | [56 empty] | ◆ | [6 empty] | ◆ | ◆ |  | ◆
[12 empty] | June 2026 | [22 empty] | July 2026 | [30 empty] | August 2026
| Task ID | Workstream | Task | Responsible | Accountable | Start | Finish | Days | Status | Dependencies | Evidence / acceptance | time axis 2026-06-08 to 2026-08-14
| GOV-01 | GOV | Proposal handoff and assessed build gate established | Tamer | Tamer | 2026-06-08 | 2026-06-08 | 1 | Done |  | Proposal artifact and fixed deadline retained — proposal/Pitch-Deck-June-8.pptx; T1 | bar: 2026-08-12
| GOV-02 | GOV | Initial governance framework created | Tamer, Dan | Tamer | 2026-06-09 | 2026-06-16 | 8 | Done |  | Kanban, Gantt and RACI committed — Commit 5c4daba; T7, T8, D3 | bar: 2026-06-09 to 2026-06-16; 2026-08-12
| GOV-03 | GOV | BRD v1.0 reconciled to delivered prototype | Nick | Tamer | 2026-06-09 | 2026-06-21 | 13 | Done |  | Versioned BRD baseline exists — docs/business-requirements.md; 3b3e82e; T1 | bar: 2026-06-09 to 2026-06-21; 2026-08-12
| PRD-01 | PRD | End-to-end operating workflow documented | Dan | Dan | 2026-06-09 | 2026-06-21 | 13 | Done |  | Happy path and verification layers documented — docs/Flow Guidance/operational-flow-v1.md; D1 | bar: 2026-06-09 to 2026-06-21; 2026-08-12
| PRD-02 | PRD | Deal, state and deterministic release rules implemented | Nick, Dan | Dan | 2026-06-15 | 2026-06-28 | 14 | Done |  | app/lib/escrow/rules.ts contains 428 lines and grades DOC-01–DOC-06 using GRADE, CROSS and FLAG rule kinds; relevant application tests pass — Commit 73f1bf7; N4, D1 | bar: 2026-06-15 to 2026-06-28; 2026-08-12
| TEC-01 | TEC | Escrow smart contract implemented | Nick, Dan | Nick | 2026-06-15 | 2026-07-05 | 21 | Done |  | contracts/contracts/Escrow.sol, tests and Ignition deployment module exist; forced compilation from source succeeds — 36222dd; N1 | bar: 2026-06-15 to 2026-07-05; 2026-08-12
| TEC-02 | TEC | Contract tests and unfunded cancellation path authored | Dan | Nick | 2026-06-29 | 2026-07-10 | 12 | Done |  | Six test files cover happy path, access control, state guards, refund, release/pause and cancellation; 21/21 pass in the standard compiled run — 36222dd, a186f98; verified 12 Aug; N1 | bar: 2026-06-29 to 2026-07-10; 2026-08-12
| TEC-03 | TEC | Off-chain store, API and rule-engine core implemented | Nick, Dan | Nick | 2026-06-22 | 2026-07-19 | 28 | Done |  | 28 API route handlers and the lifecycle/rules core exist — 73f1bf7, 6515a51; N2, N3, D5 | bar: 2026-06-22 to 2026-07-19; 2026-08-12
| TEC-04 | TEC | Buyer/seller lifecycle wired to real deal state | Nick, Dan | Nick | 2026-07-06 | 2026-07-19 | 14 | Done |  | Fund, submit and verdict journeys merged — 06efff6, fcdfaad; N2, N3 | bar: 2026-07-06 to 2026-07-19; 2026-08-12
| TEC-05 | TEC | Objection, refund and audit paths implemented | Dan | Nick | 2026-07-20 | 2026-08-02 | 14 | Done |  | Objection withdrawal, refund and audit commits exist — 5688cc3, 77cf5f6; N2, D5 | bar: 2026-07-20 to 2026-08-02; 2026-08-12
| TEC-06 | TEC | SQL persistence, account auth and SIWE implemented | Dan, Nick | Nick | 2026-07-13 | 2026-08-02 | 21 | Done |  | Prisma persistence, server sessions and SIWE wallet linking are present; application suite passes — f8cc7a9, 3123538, a2052a2; N2, N3 | bar: 2026-07-13 to 2026-08-02; 2026-08-12
| TEC-07 | TEC | Base Sepolia deployment evidence created | Dan | Nick | 2026-06-30 | 2026-07-05 | 6 | Done |  | Deployment record identifies Base Sepolia chain ID 84532 and real test USDC configuration — c4887db, 3e9b4ed; N1 | bar: 2026-06-30 to 2026-07-05; 2026-08-12
| TEC-08 | TEC | KYB data collection and onboarding gate implemented | Dan | Nick | 2026-07-20 | 2026-08-02 | 14 | Done |  | Unonboarded companies are blocked from deal creation — 10d3730, dc1de9f; B1/N2 | bar: 2026-07-20 to 2026-08-02; 2026-08-12
| UX-01 | UX | UX foundation and dashboard flows implemented | Mo | Mo | 2026-06-22 | 2026-07-05 | 14 | Done |  | Landing page and dashboard flows committed — 6dbc53a; M1, M2 | bar: 2026-06-22 to 2026-07-05; 2026-08-12
| UX-02 | UX | Role-separated buyer and seller journeys implemented | Mo, Nick | Mo | 2026-07-06 | 2026-07-19 | 14 | Done |  | Role isolation and wizard wiring merged — 95cfb0b, 06efff6; M1, M2 | bar: 2026-07-06 to 2026-07-19; 2026-08-12
| UX-03 | UX | Consolidated multi-deal dashboard assembled | Mo, Dan | Mo | 2026-07-20 | 2026-08-02 | 14 | Done |  | Refined dashboard merged with lifecycle work — e09bd51, 3779262, c61b1a6; M1–M3 | bar: 2026-07-20 to 2026-08-02; 2026-08-12
| RISK-01 | RISK | UCP 600 and Incoterms source pack assembled | Badhri | Badhri | 2026-06-09 | 2026-06-14 | 6 | Done |  | Source documents and Markdown references exist — 5fe28c1; B4 | bar: 2026-06-09 to 2026-06-14; 2026-08-12
| RISK-02 | RISK | Legal-risk register developed | Badhri | Badhri | 2026-06-09 | 2026-06-28 | 20 | Done |  | Legal-risk artifact and update history exist — docs/legal-risk.md; 7b18837; B1–B4 | bar: 2026-06-09 to 2026-06-28; 2026-08-12
| RISK-03 | RISK | Operational verification model documented | Dan, Badhri | Badhri | 2026-06-15 | 2026-07-05 | 21 | Done |  | Workflow and verification model artifacts exist — docs/verification-model-v2.md; D1, D2 | bar: 2026-06-15 to 2026-07-05; 2026-08-12
| RISK-04 | RISK | Trade-document template catalogue assembled | Badhri | Badhri | 2026-06-22 | 2026-07-19 | 28 | Done |  | Structured document-template catalogue exists — docs/document-templates.md; 28c6968; B3, D2 | bar: 2026-06-22 to 2026-07-19; 2026-08-12
| RISK-05 | RISK | UAE licensing and corridor analysis documented | Badhri, Tamer | Badhri | 2026-06-22 | 2026-07-12 | 21 | Done |  | UAE licensing research artifact exists — docs/Dubai_Fintech_License_Requirements.md; B4, B5 | bar: 2026-06-22 to 2026-07-12; 2026-08-12
| BUS-01 | BUS | Financial model refined | Conrad | Conrad | 2026-06-09 | 2026-07-05 | 27 | Done |  | Five-year model artifact exists — financial-projections/Blockmediary_Financial_Model_FullRisk.xlsx; 56e5e6a; C1, C2 | bar: 2026-06-09 to 2026-07-05; 2026-08-12
| BUS-02 | BUS | Customer-demographic analysis produced | Mo, Conrad | Mo | 2026-06-09 | 2026-06-28 | 20 | Done |  | Customer profile research exists — project-initialisation/customer-demographics.md; 99400ce; M5, M7 | bar: 2026-06-09 to 2026-06-28; 2026-08-12
| BUS-06 | BUS | Original Business Model Canvas produced | Tamer, Conrad, Mo | Conrad | 2026-06-08 | 2026-06-08 | 1 | Done |  | Eight-block canvas exists with opportunity, market, revenue, cost, channels and competition — proposal/business-model-slide.md; T2 | bar: 2026-08-12
◆ | GOV-04 | GOV | TRD and A1–A8 acceptance baseline reconciled | Nick | Tamer | 2026-06-15 | 2026-08-12 | 59 | Review |  | Run and record every acceptance case; remove any remaining delivered-status contradiction — docs/technical-requirements.md; 42aa948; T1 | bar: 2026-06-15 to 2026-08-12
◆ | PRD-03 | PRD | Full document-pack and corridor release rules aligned | Nick, Badhri | Dan | 2026-06-22 | 2026-08-12 | 52 | Review |  | Cold test required documents and reconcile BRD language with implemented pack — 9e697cf, f9bbd27, 498751d; N4/B5 | bar: 2026-06-22 to 2026-08-12
◆ | PRD-04 | PRD | Final product-to-pitch traceability approved | Dan, Tamer | Dan | 2026-07-27 | 2026-08-12 | 17 | Review |  | Every script claim maps to delivered evidence or roadmap label — BRD/TRD reconciliation; commit 42aa948; saved claims register still pending under DEC-13; T5 | bar: 2026-07-27 to 2026-08-12
◆ | TEC-09 | TEC | Technical acceptance A1–A8 completed | Nick, Dan | Nick | 2026-08-03 | 2026-08-12 | 10 | Review |  | A1 achieved: forced source compile and 21/21 contract tests pass. Supporting evidence: 187/187 application tests pass. Open: A2–A7 integrated authenticated walkthrough, A8 control record, production build and lint — Test/compile evidence 12 Aug; TRD Section 11; N1–N4/D5 | bar: 2026-08-03 to 2026-08-12
◆ | TEC-10 | TEC | Repository sync and clean-build reproducibility verified | Nick | Nick | 2026-08-10 | 2026-08-12 | 3 | Review |  | Known failing: Prisma postinstall loads untracked app/.env; no app-level example exists; npm and pnpm lockfiles compete; production build and focused lint fail — Configuration/build/lint evidence 12 Aug; D3 | bar: 2026-08-10 to 2026-08-12
◆ | RISK-06 | RISK | Legal/compliance claims and delivery boundary signed off | Badhri, Tamer | Badhri | 2026-08-03 | 2026-08-12 | 10 | Review |  | No legal-advice claim; live screening, TEA and examiner functions labelled roadmap — Legal and document sources; B1–B4 | bar: 2026-08-03 to 2026-08-12
| BUS-03 | BUS | Competitor analysis verified for pitch use | Badhri, Mo | Mo | 2026-06-15 | 2026-08-12 | 59 | Review |  | Fees, automation and corridor claims are source-checked and not overstated — docs/Competitor-analysis.md; 9b9601b; T10 | bar: 2026-06-15 to 2026-08-12
| BUS-04 | BUS | Pricing, unit economics, funding ask and beachhead approved | Conrad, Mo | Conrad | 2026-06-15 | 2026-08-12 | 59 | Review |  | One assumption set is recorded and used consistently in deck and script — Financial model and customer research; C2–C4/M5/M8 | bar: 2026-06-15 to 2026-08-12
| GOV-05 | GOV | Governance, decision, risk and blocker control maintained through submission | Tamer, Dan | Tamer | 2026-06-09 | 2026-08-14 | 67 | Doing | All workstreams; T7, T8, D3 | Daily critical-path update; decisions and variances reflected in all reports
◆ | UX-04 | UX | /dashboard approved as the single recorded product route | Mo, Dan | Mo | 2026-08-03 | 2026-08-11 | 9 | Doing | TEC-09; M1–M3 | Overdue at 12 Aug: team decision, route allowlist, demo accounts and exact click path must be recorded; legacy/dev/admin navigation must be excluded | bar: 2026-08-03 to 2026-08-12
◆ | UX-05 | UX | Demo polish, empty/error states and accessibility pass completed | Mo | Mo | 2026-08-03 | 2026-08-12 | 10 | Doing | UX-04, TEC-09; M4 | Recorded path has no broken/legacy navigation; key text and states are legible | bar: 2026-08-03 to 2026-08-12
◆ | BUS-05 | BUS | Final real-value and commercial narrative locked | Conrad, Mo, Tamer | Conrad | 2026-07-27 | 2026-08-12 | 17 | Doing | BUS-03, BUS-04; T2, T9 | Problem, beachhead, differentiation, business model, evidence and ask use one approved story | bar: 2026-07-27 to 2026-08-12
◆ | BUS-07 | BUS | Evidence-aligned BMC v2 approved for final pitch | Conrad, Tamer, Mo, Badhri | Conrad | 2026-08-12 | 2026-08-12 | 1 | Doing | BUS-03, BUS-04, BUS-06; T2 | Zero float: close before SUB-01 or remove unresolved BMC claims; narrow beachhead, financing distinction, minimum-plus-% fee and delivered/roadmap split required | bar: 2026-08-12
◆ | SUB-01 | SUB | Five-minute deck and timed script locked | Tamer, all leads | Tamer | 2026-07-27 | 2026-08-12 | 17 | Doing | PRD-04, RISK-06, BUS-05; D4 | Script is under five minutes and weights real value above technical detail | bar: 2026-07-27 to 2026-08-12
◆ | SUB-02 | SUB | Deterministic demo runbook and seed/reset procedure completed | Dan, Nick | Dan | 2026-08-03 | 2026-08-12 | 10 | To Do | TEC-09, UX-04; D4 | Another member can reproduce the happy path without improvisation | bar: 2026-08-03 to 2026-08-12
● | SUB-03 | SUB | Two cold end-to-end rehearsals completed | Dan, Mo | Dan | 2026-08-10 | 2026-08-13 | 4 | To Do | SUB-01, SUB-02 | Both runs complete within the timed allocation; defects and workarounds logged | bar: 2026-08-10 to 2026-08-13
● | SUB-04 | SUB | Primary presentation recorded, edited and captioned | Dan, Mo, Tamer | Dan | 2026-08-12 | 2026-08-13 | 2 | To Do | SUB-03 | Final render is clear, below five minutes and uses approved product claims | bar: 2026-08-12 to 2026-08-13
● | SUB-05 | SUB | Fallback demo recording retained | Dan, Nick | Dan | 2026-08-12 | 2026-08-13 | 2 | To Do | SUB-02, TEC-09 | Standalone fallback opens and shows the approved workflow | bar: 2026-08-12 to 2026-08-13
● | SUB-06 | SUB | Video link, PDF and permission QA completed independently | Tamer, independent checker (TBD) | Tamer | 2026-08-13 | 2026-08-14 | 2 | To Do | SUB-04, SUB-05 | Link works in private browser; PDF renders; filename and permissions pass | bar: 2026-08-12 to 2026-08-14
● | SUB-07 | SUB | Main group video submission completed | Tamer | Tamer | 2026-08-14 | 2026-08-14 | 1 | To Do | SUB-06 | Submission receipt and final artifacts preserved | bar: 2026-08-12
| DEF-01 | Deferred | AI/OCR document extraction | [5 empty] | Deferred |  | Not required for a credible deterministic prototype; delivered claim would be misleading — Extraction accuracy evaluation, failure handling and integrated acceptance | bar: 2026-08-12
| DEF-02 | Deferred | Live KYC/KYB and sanctions providers | [5 empty] | Deferred |  | Provider, jurisdiction and operational responsibilities are unresolved — Provider selection, contracts, test environment and compliance approval | bar: 2026-08-12
| DEF-03 | Deferred | Generated or counsel-approved Trade Escrow Agreement | [5 empty] | Deferred |  | Legal wrapper is not production-ready — Jurisdiction choice, qualified legal review and signed operating model | bar: 2026-08-12
| DEF-04 | Deferred | Human document-examiner console and network | [5 empty] | Deferred |  | Research exists but the operating service is not delivered — SOP, permissions, audit model, staffing and tested console | bar: 2026-08-12
| DEF-05 | Deferred | Electronic bill-of-lading title transfer | [5 empty] | Deferred |  | Legal and technical scope exceeds the academic MVP — eBL provider/legal framework and end-to-end title controls | bar: 2026-08-12
| DEF-06 | Deferred | Mainnet, custody and production hardening | [5 empty] | Deferred |  | Testnet/local evidence is sufficient for the assessment prototype — Security review, key management, monitoring and production runbook | bar: 2026-08-12
| DEF-07 | Deferred | Partner logistics, bank and compliance APIs | [5 empty] | Deferred |  | External coordination and reliability are outside the submission window — Selected partners, sandbox access, contracts and integration tests | bar: 2026-08-12
| DEF-08 | Deferred | User-facing multi-agent runtime | [5 empty] | Deferred |  | Agent scaffold is not the same as a delivered product runtime — Approved use cases, API integration, safety controls and UX acceptance | bar: 2026-08-12
Note on M8: Milestone: Proposal handoff — 08 June 2026
Note on BR8: Milestone: Base Sepolia evidence — 04 August 2026
Note on BY8: Milestone: Scope / route freeze — 11 August 2026
Note on BZ8: Milestone: Acceptance / claim freeze — 12 August 2026
Note on CB8: Milestone: Main group submission — 14 August 2026
Note on M10: Monday, 08 June 2026 — Proposal handoff
Note on N10: Tuesday, 09 June 2026
Note on O10: Wednesday, 10 June 2026
Note on P10: Thursday, 11 June 2026
Note on Q10: Friday, 12 June 2026
Note on R10: Saturday, 13 June 2026
Note on S10: Sunday, 14 June 2026
Note on T10: Monday, 15 June 2026
Note on U10: Tuesday, 16 June 2026
Note on V10: Wednesday, 17 June 2026
Note on W10: Thursday, 18 June 2026
Note on X10: Friday, 19 June 2026
Note on Y10: Saturday, 20 June 2026
Note on Z10: Sunday, 21 June 2026
Note on AA10: Monday, 22 June 2026
Note on AB10: Tuesday, 23 June 2026
Note on AC10: Wednesday, 24 June 2026
Note on AD10: Thursday, 25 June 2026
Note on AE10: Friday, 26 June 2026
Note on AF10: Saturday, 27 June 2026
Note on AG10: Sunday, 28 June 2026
Note on AH10: Monday, 29 June 2026
Note on AI10: Tuesday, 30 June 2026
Note on AJ10: Wednesday, 01 July 2026
Note on AK10: Thursday, 02 July 2026
Note on AL10: Friday, 03 July 2026
Note on AM10: Saturday, 04 July 2026
Note on AN10: Sunday, 05 July 2026
Note on AO10: Monday, 06 July 2026
Note on AP10: Tuesday, 07 July 2026
Note on AQ10: Wednesday, 08 July 2026
Note on AR10: Thursday, 09 July 2026
Note on AS10: Friday, 10 July 2026
Note on AT10: Saturday, 11 July 2026
Note on AU10: Sunday, 12 July 2026
Note on AV10: Monday, 13 July 2026
Note on AW10: Tuesday, 14 July 2026
Note on AX10: Wednesday, 15 July 2026
Note on AY10: Thursday, 16 July 2026
Note on AZ10: Friday, 17 July 2026
Note on BA10: Saturday, 18 July 2026
Note on BB10: Sunday, 19 July 2026
Note on BC10: Monday, 20 July 2026
Note on BD10: Tuesday, 21 July 2026
Note on BE10: Wednesday, 22 July 2026
Note on BF10: Thursday, 23 July 2026
Note on BG10: Friday, 24 July 2026
Note on BH10: Saturday, 25 July 2026
Note on BI10: Sunday, 26 July 2026
Note on BJ10: Monday, 27 July 2026
Note on BK10: Tuesday, 28 July 2026
Note on BL10: Wednesday, 29 July 2026
Note on BM10: Thursday, 30 July 2026
Note on BN10: Friday, 31 July 2026
Note on BO10: Saturday, 01 August 2026
Note on BP10: Sunday, 02 August 2026
Note on BQ10: Monday, 03 August 2026
Note on BR10: Tuesday, 04 August 2026 — Base Sepolia evidence
Note on BS10: Wednesday, 05 August 2026
Note on BT10: Thursday, 06 August 2026
Note on BU10: Friday, 07 August 2026
Note on BV10: Saturday, 08 August 2026
Note on BW10: Sunday, 09 August 2026
Note on BX10: Monday, 10 August 2026
Note on BY10: Tuesday, 11 August 2026 — Scope / route freeze
Note on BZ10: Wednesday, 12 August 2026 — Acceptance / claim freeze
Note on CA10: Thursday, 13 August 2026
Note on CB10: Friday, 14 August 2026 — Main group submission

## Task Register
Blockmediary — Controlled Task Register
Auditable 12 August 2026 snapshot ¦ Group work only ¦ Authoritative sources: master project plan, Kanban and RACI v2.1
CONTROLLED CARDS |  |  | ACTIVE CARDS |  |  | DONE |  |  | AT ACCEPTANCE |  |  | IN FLIGHT |  |  | DEFERRED
52 |  |  | 44 |  |  | 24 |  |  | 8 |  |  | 6 |  |  | 8
Task ID | Workstream | Task / outcome | Responsible owner(s) | Accountable | Baseline start | Baseline finish | Current due | Duration (days) | Status | Progress | Observed date | Source timing | Dependencies / aliases | Acceptance and evidence | Criticality | Overdue control | Source report
GOV-01 | GOV | Proposal handoff and assessed build gate established | Tamer | Tamer | 2026-06-08 | 2026-06-08 |  | 1 | Done | 100% | 2026-06-08 | Planned: 8 Jun ¦ Observed: 8 Jun |  | Proposal artifact and fixed deadline retained — proposal/Pitch-Deck-June-8.pptx; T1 |  |  | Master Kanban — Done
GOV-02 | GOV | Initial governance framework created | Tamer, Dan | Tamer | 2026-06-09 | 2026-06-16 |  | 8 | Done | 100% | 2026-06-17 | Planned: 9–16 Jun ¦ Observed: 17 Jun |  | Kanban, Gantt and RACI committed — Commit 5c4daba; T7, T8, D3 |  |  | Master Kanban — Done
GOV-03 | GOV | BRD v1.0 reconciled to delivered prototype | Nick | Tamer | 2026-06-09 | 2026-06-21 |  | 13 | Done | 100% | 2026-08-09 | Planned: 9–21 Jun ¦ Observed: 9 Aug |  | Versioned BRD baseline exists — docs/business-requirements.md; 3b3e82e; T1 |  |  | Master Kanban — Done
PRD-01 | PRD | End-to-end operating workflow documented | Dan | Dan | 2026-06-09 | 2026-06-21 |  | 13 | Done | 100% | 2026-06-25 | Planned: 9–21 Jun ¦ Observed: 25 Jun |  | Happy path and verification layers documented — docs/Flow Guidance/operational-flow-v1.md; D1 |  |  | Master Kanban — Done
PRD-02 | PRD | Deal, state and deterministic release rules implemented | Nick, Dan | Dan | 2026-06-15 | 2026-06-28 |  | 14 | Done | 100% | 2026-07-10 | Planned: 15–28 Jun ¦ Observed: 10 Jul |  | app/lib/escrow/rules.ts contains 428 lines and grades DOC-01–DOC-06 using GRADE, CROSS and FLAG rule kinds; relevant application tests pass — Commit 73f1bf7; N4, D1 |  |  | Master Kanban — Done
TEC-01 | TEC | Escrow smart contract implemented | Nick, Dan | Nick | 2026-06-15 | 2026-07-05 |  | 21 | Done | 100% | 2026-07-05 | Planned: 15 Jun–5 Jul ¦ Observed: 5 Jul |  | contracts/contracts/Escrow.sol, tests and Ignition deployment module exist; forced compilation from source succeeds — 36222dd; N1 |  |  | Master Kanban — Done
TEC-02 | TEC | Contract tests and unfunded cancellation path authored | Dan | Nick | 2026-06-29 | 2026-07-10 |  | 12 | Done | 100% | 2026-07-10 | Planned: 29 Jun–10 Jul ¦ Observed: 10 Jul |  | Six test files cover happy path, access control, state guards, refund, release/pause and cancellation; 21/21 pass in the standard compiled run — 36222dd, a186f98; verified 12 Aug; N1 |  |  | Master Kanban — Done
TEC-03 | TEC | Off-chain store, API and rule-engine core implemented | Nick, Dan | Nick | 2026-06-22 | 2026-07-19 |  | 28 | Done | 100% | 2026-07-10 | Planned: 22 Jun–19 Jul ¦ Observed: 10 Jul |  | 28 API route handlers and the lifecycle/rules core exist — 73f1bf7, 6515a51; N2, N3, D5 |  |  | Master Kanban — Done
TEC-04 | TEC | Buyer/seller lifecycle wired to real deal state | Nick, Dan | Nick | 2026-07-06 | 2026-07-19 |  | 14 | Done | 100% | 2026-07-13 | Planned: 6–19 Jul ¦ Observed: 13 Jul |  | Fund, submit and verdict journeys merged — 06efff6, fcdfaad; N2, N3 |  |  | Master Kanban — Done
TEC-05 | TEC | Objection, refund and audit paths implemented | Dan | Nick | 2026-07-20 | 2026-08-02 |  | 14 | Done | 100% | 2026-07-31 | Planned: 20 Jul–2 Aug ¦ Observed: 31 Jul |  | Objection withdrawal, refund and audit commits exist — 5688cc3, 77cf5f6; N2, D5 |  |  | Master Kanban — Done
TEC-06 | TEC | SQL persistence, account auth and SIWE implemented | Dan, Nick | Nick | 2026-07-13 | 2026-08-02 |  | 21 | Done | 100% | 2026-08-05 | Planned: 13 Jul–2 Aug ¦ Observed: 5 Aug |  | Prisma persistence, server sessions and SIWE wallet linking are present; application suite passes — f8cc7a9, 3123538, a2052a2; N2, N3 |  |  | Master Kanban — Done
TEC-07 | TEC | Base Sepolia deployment evidence created | Dan | Nick | 2026-06-30 | 2026-07-05 |  | 6 | Done | 100% | 2026-08-10 | Planned: 30 Jun–5 Jul ¦ Observed: 4 Aug deployment; 10 Aug merge |  | Deployment record identifies Base Sepolia chain ID 84532 and real test USDC configuration — c4887db, 3e9b4ed; N1 |  |  | Master Kanban — Done
TEC-08 | TEC | KYB data collection and onboarding gate implemented | Dan | Nick | 2026-07-20 | 2026-08-02 |  | 14 | Done | 100% | 2026-08-08 | Planned: 20 Jul–2 Aug ¦ Observed: 8 Aug |  | Unonboarded companies are blocked from deal creation — 10d3730, dc1de9f; B1/N2 |  |  | Master Kanban — Done
UX-01 | UX | UX foundation and dashboard flows implemented | Mo | Mo | 2026-06-22 | 2026-07-05 |  | 14 | Done | 100% | 2026-07-09 | Planned: 22 Jun–5 Jul ¦ Observed: 9 Jul |  | Landing page and dashboard flows committed — 6dbc53a; M1, M2 |  |  | Master Kanban — Done
UX-02 | UX | Role-separated buyer and seller journeys implemented | Mo, Nick | Mo | 2026-07-06 | 2026-07-19 |  | 14 | Done | 100% | 2026-07-13 | Planned: 6–19 Jul ¦ Observed: 13 Jul |  | Role isolation and wizard wiring merged — 95cfb0b, 06efff6; M1, M2 |  |  | Master Kanban — Done
UX-03 | UX | Consolidated multi-deal dashboard assembled | Mo, Dan | Mo | 2026-07-20 | 2026-08-02 |  | 14 | Done | 100% | 2026-08-08 | Planned: 20 Jul–2 Aug ¦ Observed: 8 Aug |  | Refined dashboard merged with lifecycle work — e09bd51, 3779262, c61b1a6; M1–M3 |  |  | Master Kanban — Done
RISK-01 | RISK | UCP 600 and Incoterms source pack assembled | Badhri | Badhri | 2026-06-09 | 2026-06-14 |  | 6 | Done | 100% | 2026-06-14 | Planned: 9–14 Jun ¦ Observed: 14 Jun |  | Source documents and Markdown references exist — 5fe28c1; B4 |  |  | Master Kanban — Done
RISK-02 | RISK | Legal-risk register developed | Badhri | Badhri | 2026-06-09 | 2026-06-28 |  | 20 | Done | 100% | 2026-06-23 | Planned: 9–28 Jun ¦ Observed: 23 Jun |  | Legal-risk artifact and update history exist — docs/legal-risk.md; 7b18837; B1–B4 |  |  | Master Kanban — Done
RISK-03 | RISK | Operational verification model documented | Dan, Badhri | Badhri | 2026-06-15 | 2026-07-05 |  | 21 | Done | 100% | 2026-07-01 | Planned: 15 Jun–5 Jul ¦ Observed: 1 Jul |  | Workflow and verification model artifacts exist — docs/verification-model-v2.md; D1, D2 |  |  | Master Kanban — Done
RISK-04 | RISK | Trade-document template catalogue assembled | Badhri | Badhri | 2026-06-22 | 2026-07-19 |  | 28 | Done | 100% | 2026-08-05 | Planned: 22 Jun–19 Jul ¦ Observed: 5 Aug |  | Structured document-template catalogue exists — docs/document-templates.md; 28c6968; B3, D2 |  |  | Master Kanban — Done
RISK-05 | RISK | UAE licensing and corridor analysis documented | Badhri, Tamer | Badhri | 2026-06-22 | 2026-07-12 |  | 21 | Done | 100% | 2026-07-22 | Planned: 22 Jun–12 Jul ¦ Observed: 22 Jul |  | UAE licensing research artifact exists — docs/Dubai_Fintech_License_Requirements.md; B4, B5 |  |  | Master Kanban — Done
BUS-01 | BUS | Financial model refined | Conrad | Conrad | 2026-06-09 | 2026-07-05 |  | 27 | Done | 100% | 2026-07-01 | Planned: 9 Jun–5 Jul ¦ Observed: 1 Jul |  | Five-year model artifact exists — financial-projections/Blockmediary_Financial_Model_FullRisk.xlsx; 56e5e6a; C1, C2 |  |  | Master Kanban — Done
BUS-02 | BUS | Customer-demographic analysis produced | Mo, Conrad | Mo | 2026-06-09 | 2026-06-28 |  | 20 | Done | 100% | 2026-07-01 | Planned: 9–28 Jun ¦ Observed: 1 Jul |  | Customer profile research exists — project-initialisation/customer-demographics.md; 99400ce; M5, M7 |  |  | Master Kanban — Done
BUS-06 | BUS | Original Business Model Canvas produced | Tamer, Conrad, Mo | Conrad | 2026-06-08 | 2026-06-08 |  | 1 | Done | 100% | 2026-06-08 | Planned: G0 handoff ¦ Observed: 8 Jun baseline artifact |  | Eight-block canvas exists with opportunity, market, revenue, cost, channels and competition — proposal/business-model-slide.md; T2 |  |  | Master Kanban — Done
GOV-04 | GOV | TRD and A1–A8 acceptance baseline reconciled | Nick | Tamer | 2026-06-15 | 2026-06-28 | 2026-08-12 | 59 | Review | 85% | 2026-08-11 | Planned: 15–28 Jun ¦ Observed: 11 Aug |  | Run and record every acceptance case; remove any remaining delivered-status contradiction — docs/technical-requirements.md; 42aa948; T1 | Zero float | DUE | Master Kanban — Review
PRD-03 | PRD | Full document-pack and corridor release rules aligned | Nick, Badhri | Dan | 2026-06-22 | 2026-07-05 | 2026-08-12 | 52 | Review | 85% | 2026-08-09 | Planned: 22 Jun–5 Jul ¦ Observed: 9 Aug |  | Cold test required documents and reconcile BRD language with implemented pack — 9e697cf, f9bbd27, 498751d; N4/B5 | Zero float | DUE | Master Kanban — Review
PRD-04 | PRD | Final product-to-pitch traceability approved | Dan, Tamer | Dan | 2026-07-27 | 2026-08-11 | 2026-08-12 | 17 | Review | 85% | 2026-08-11 | Planned: 27 Jul–11 Aug ¦ Observed: 11 Aug draft |  | Every script claim maps to delivered evidence or roadmap label — BRD/TRD reconciliation; commit 42aa948; saved claims register still pending under DEC-13; T5 | Zero float | DUE | Master Kanban — Review
TEC-09 | TEC | Technical acceptance A1–A8 completed | Nick, Dan | Nick | 2026-08-03 | 2026-08-11 | 2026-08-12 | 10 | Review | 85% | 2026-08-12 | Planned: 3–11 Aug ¦ Observed: Partial on 12 Aug |  | A1 achieved: forced source compile and 21/21 contract tests pass. Supporting evidence: 187/187 application tests pass. Open: A2–A7 integrated authenticated walkthrough, A8 control record, production build and lint — Test/compile evidence 12 Aug; TRD Section 11; N1–N4/D5 | Zero float | DUE | Master Kanban — Review
TEC-10 | TEC | Repository sync and clean-build reproducibility verified | Nick | Nick | 2026-08-10 | 2026-08-12 | 2026-08-12 | 3 | Review | 85% | 2026-08-12 | Planned: 10–12 Aug ¦ Observed: Failure confirmed 12 Aug |  | Known failing: Prisma postinstall loads untracked app/.env; no app-level example exists; npm and pnpm lockfiles compete; production build and focused lint fail — Configuration/build/lint evidence 12 Aug; D3 | Zero float | DUE | Master Kanban — Review
RISK-06 | RISK | Legal/compliance claims and delivery boundary signed off | Badhri, Tamer | Badhri | 2026-08-03 | 2026-08-12 | 2026-08-12 | 10 | Review | 85% |  | Planned: 3–12 Aug ¦ Observed: Research exists |  | No legal-advice claim; live screening, TEA and examiner functions labelled roadmap — Legal and document sources; B1–B4 | Zero float | DUE | Master Kanban — Review
BUS-03 | BUS | Competitor analysis verified for pitch use | Badhri, Mo | Mo | 2026-06-15 | 2026-07-05 | 2026-08-12 | 59 | Review | 85% | 2026-08-04 | Planned: 15 Jun–5 Jul ¦ Observed: 4 Aug |  | Fees, automation and corridor claims are source-checked and not overstated — docs/Competitor-analysis.md; 9b9601b; T10 |  | DUE | Master Kanban — Review
BUS-04 | BUS | Pricing, unit economics, funding ask and beachhead approved | Conrad, Mo | Conrad | 2026-06-15 | 2026-07-12 | 2026-08-12 | 59 | Review | 85% |  | Planned: 15 Jun–12 Jul ¦ Observed: Model/research exist |  | One assumption set is recorded and used consistently in deck and script — Financial model and customer research; C2–C4/M5/M8 |  | DUE | Master Kanban — Review
GOV-05 | GOV | Governance, decision, risk and blocker control maintained through submission | Tamer, Dan | Tamer | 2026-06-09 | 2026-08-14 | 2026-08-14 | 67 | Doing | 55% |  | Planned: 9 Jun–14 Aug | All workstreams; T7, T8, D3 | Daily critical-path update; decisions and variances reflected in all reports |  |  | Master Kanban — Doing
UX-04 | UX | /dashboard approved as the single recorded product route | Mo, Dan | Mo | 2026-08-03 | 2026-08-09 | 2026-08-11 | 9 | Doing | 55% |  | Planned: 3–9 Aug | TEC-09; M1–M3 | Overdue at 12 Aug: team decision, route allowlist, demo accounts and exact click path must be recorded; legacy/dev/admin navigation must be excluded | Zero float | OVERDUE | Master Kanban — Doing
UX-05 | UX | Demo polish, empty/error states and accessibility pass completed | Mo | Mo | 2026-08-03 | 2026-08-12 | 2026-08-12 | 10 | Doing | 55% |  | Planned: 3–12 Aug | UX-04, TEC-09; M4 | Recorded path has no broken/legacy navigation; key text and states are legible | Zero float | DUE | Master Kanban — Doing
BUS-05 | BUS | Final real-value and commercial narrative locked | Conrad, Mo, Tamer | Conrad | 2026-07-27 | 2026-08-12 | 2026-08-12 | 17 | Doing | 55% |  | Planned: 27 Jul–12 Aug | BUS-03, BUS-04; T2, T9 | Problem, beachhead, differentiation, business model, evidence and ask use one approved story | Zero float | DUE | Master Kanban — Doing
BUS-07 | BUS | Evidence-aligned BMC v2 approved for final pitch | Conrad, Tamer, Mo, Badhri | Conrad | 2026-08-12 | 2026-08-12 | 2026-08-12 | 1 | Doing | 55% |  | Planned: 12 Aug | BUS-03, BUS-04, BUS-06; T2 | Zero float: close before SUB-01 or remove unresolved BMC claims; narrow beachhead, financing distinction, minimum-plus-% fee and delivered/roadmap split required | Zero float | DUE | Master Kanban — Doing
SUB-01 | SUB | Five-minute deck and timed script locked | Tamer, all leads | Tamer | 2026-07-27 | 2026-08-09 | 2026-08-12 | 17 | Doing | 55% |  | Planned: 27 Jul–9 Aug | PRD-04, RISK-06, BUS-05; D4 | Script is under five minutes and weights real value above technical detail | Zero float | DUE | Master Kanban — Doing
SUB-02 | SUB | Deterministic demo runbook and seed/reset procedure completed | Dan, Nick | Dan | 2026-08-03 | 2026-08-12 | 2026-08-12 | 10 | To Do | 0% |  | Planned: 3–12 Aug | TEC-09, UX-04; D4 | Another member can reproduce the happy path without improvisation | Zero float | DUE | Master Kanban — To Do
SUB-03 | SUB | Two cold end-to-end rehearsals completed | Dan, Mo | Dan | 2026-08-10 | 2026-08-13 | 2026-08-13 | 4 | To Do | 0% |  | Planned: 10–13 Aug | SUB-01, SUB-02 | Both runs complete within the timed allocation; defects and workarounds logged | Critical path |  | Master Kanban — To Do
SUB-04 | SUB | Primary presentation recorded, edited and captioned | Dan, Mo, Tamer | Dan | 2026-08-12 | 2026-08-13 | 2026-08-13 | 2 | To Do | 0% |  | Planned: 12–13 Aug | SUB-03 | Final render is clear, below five minutes and uses approved product claims | Critical path |  | Master Kanban — To Do
SUB-05 | SUB | Fallback demo recording retained | Dan, Nick | Dan | 2026-08-12 | 2026-08-13 | 2026-08-13 | 2 | To Do | 0% |  | Planned: 12–13 Aug | SUB-02, TEC-09 | Standalone fallback opens and shows the approved workflow | Critical path |  | Master Kanban — To Do
SUB-06 | SUB | Video link, PDF and permission QA completed independently | Tamer, independent checker (TBD) | Tamer | 2026-08-13 | 2026-08-14 | 2026-08-14 | 2 | To Do | 0% |  | Planned: 13–14 Aug | SUB-04, SUB-05 | Link works in private browser; PDF renders; filename and permissions pass | Critical path |  | Master Kanban — To Do
SUB-07 | SUB | Main group video submission completed | Tamer | Tamer | 2026-08-14 | 2026-08-14 | 2026-08-14 | 1 | To Do | 0% |  | Planned: 14 Aug | SUB-06 | Submission receipt and final artifacts preserved | Critical path |  | Master Kanban — To Do
DEF-01 | Deferred | AI/OCR document extraction | [6 empty] | Deferred | 0% |  | Planned: not scheduled |  | Not required for a credible deterministic prototype; delivered claim would be misleading — Extraction accuracy evaluation, failure handling and integrated acceptance |  |  | Master Kanban — Deferred / post-MVP
DEF-02 | Deferred | Live KYC/KYB and sanctions providers | [6 empty] | Deferred | 0% |  | Planned: not scheduled |  | Provider, jurisdiction and operational responsibilities are unresolved — Provider selection, contracts, test environment and compliance approval |  |  | Master Kanban — Deferred / post-MVP
DEF-03 | Deferred | Generated or counsel-approved Trade Escrow Agreement | [6 empty] | Deferred | 0% |  | Planned: not scheduled |  | Legal wrapper is not production-ready — Jurisdiction choice, qualified legal review and signed operating model |  |  | Master Kanban — Deferred / post-MVP
DEF-04 | Deferred | Human document-examiner console and network | [6 empty] | Deferred | 0% |  | Planned: not scheduled |  | Research exists but the operating service is not delivered — SOP, permissions, audit model, staffing and tested console |  |  | Master Kanban — Deferred / post-MVP
DEF-05 | Deferred | Electronic bill-of-lading title transfer | [6 empty] | Deferred | 0% |  | Planned: not scheduled |  | Legal and technical scope exceeds the academic MVP — eBL provider/legal framework and end-to-end title controls |  |  | Master Kanban — Deferred / post-MVP
DEF-06 | Deferred | Mainnet, custody and production hardening | [6 empty] | Deferred | 0% |  | Planned: not scheduled |  | Testnet/local evidence is sufficient for the assessment prototype — Security review, key management, monitoring and production runbook |  |  | Master Kanban — Deferred / post-MVP
DEF-07 | Deferred | Partner logistics, bank and compliance APIs | [6 empty] | Deferred | 0% |  | Planned: not scheduled |  | External coordination and reliability are outside the submission window — Selected partners, sandbox access, contracts and integration tests |  |  | Master Kanban — Deferred / post-MVP
DEF-08 | Deferred | User-facing multi-agent runtime | [6 empty] | Deferred | 0% |  | Planned: not scheduled |  | Agent scaffold is not the same as a delivered product runtime — Approved use cases, API integration, safety controls and UX acceptance |  |  | Master Kanban — Deferred / post-MVP

## Milestones & Controls
Blockmediary — Milestones & Controls
Submission gates, acceptance conditions, unresolved blockers and workbook-control notes ¦ Honest pre-remediation snapshot at 12 August 2026
MILESTONE GATES
Gate date | Milestone | Accountable | Acceptance condition | Current evidence | Status | Variance / control | Marker
2026-06-08 | Proposal handoff | Tamer | Proposal evidence retained and assessed build window opened | proposal/Pitch-Deck-June-8.pptx retained | Done | On baseline | ◆
2026-08-04 | Base Sepolia deployment evidence | Nick | Deployment address, network and chain evidence retained | Base Sepolia chain ID 84532; deployment record dated 4 Aug | Done | Deployment evidence achieved; integration merge 10 Aug | ◆
2026-08-11 | Scope and demo-route freeze | Tamer | Approved /dashboard route, allowlist and exact click path | Canonical route decision not formally recorded | Overdue | Zero float at status date | ◆
2026-08-12 | Acceptance and claim freeze | Nick / Tamer | A1–A8, build/lint, BMC and domain claims accepted | A1 achieved; A2–A8, build/lint and domain approvals remain open | At risk / Partial | DEL-05 at risk; do not report remediation complete | ◆
2026-08-13 | Recording package | Dan | Two cold rehearsals, primary recording and fallback retained | Not evidenced at status date | To Do | Depends on accepted runbook and claim freeze | ◆
2026-08-14 | Main group submission | Tamer | Link, PDF and permissions independently checked; receipt retained | Future at status date | To Do | Fixed assessment deadline | ◆
CURRENT TECHNICAL AND GOVERNANCE CONTROLS
Control | State | Owner | Evidence at 12 Aug | Open requirement | Impact | Related task / risk | Truth boundary
DEL-05 Technical acceptance baseline | At risk | Nick | A1 achieved; 187/187 app tests support delivered behaviour | Complete A2–A7 walkthrough, A8 control record, clean setup, build and lint | Recording readiness not accepted | DEL-05 / TEC-09 / TEC-10 | Partially achieved only
R-01 Integrated acceptance / reproducibility | Confirmed | Nick | Clean setup/build failures reproduced | Restore reproducibility and integrated evidence | High | R-01 | Confirmed risk remains open
R-08 Cross-machine repository state | Confirmed | Nick | Untracked app/.env dependency; no app example; npm/pnpm locks compete | Correct bootstrap and verify fresh dependency-free checkout | High | R-08 / TEC-10 | Confirmed risk remains open
Contract forced source rebuild | Pass | Nick | solc 0.8.28 forced rebuild; 21/21 tests passed | Retain evidence; does not close app clean-install gate | A1 achieved | TEC-09 | Contract evidence passed
Application unit tests | Pass | Nick | 187/187 tests across 10/10 files | Integrated authenticated walkthrough still required | Supporting evidence | TEC-09 | Tests do not equal full acceptance
Clean installation | Open / Fail | Nick | Prisma postinstall expects untracked app/.env | Add reproducible environment bootstrap and select package manager | High | TEC-10 | Do not mark complete
Production build | Open / Fail | Nick | TypeScript rejected invalid named page export | Correct source and rerun from clean setup | High | TEC-10 | Do not mark complete
Focused source lint | Open / Fail | Nick | 5 errors and 12 warnings | Fix source errors; keep generated output excluded separately | Medium | TEC-09 / TEC-10 | Do not mark complete
Independent walkthrough | Open | Nick / Dan | A2–A7 integrated authenticated run not fully evidenced | Run and record accepted A1–A8 control sequence | High | TEC-09 / SUB-02 | SUB-02 remains To Do
WORKBOOK CONTROL NOTES
1 | Snapshot is honest as at 12 August 2026 before technical remediation.
2 | Scope begins at proposal handoff on 8 June and ends at the second group submission on 14 August; individual-assignment work is excluded.
3 | The Master Gantt uses reconstructed baseline start dates. Active rows extend to their explicit current due dates; the Task Register retains baseline finish and observed timing separately.
4 | Deferred items are grey, unscheduled and excluded from active completion. No dates have been invented for DEF-01–DEF-08.
5 | Active completion = Done divided by all non-deferred cards. It is a task-state indicator, not a submission-readiness score.
6 | Critical-path flags follow the plan's remaining chain. Zero-float flags identify open chain tasks due on or before the 12 August status date.
7 | The obsolete M0–M8 Gantt is excluded. The controlled IDs are GOV-, PRD-, TEC-, UX-, RISK-, BUS-, SUB- and DEF- rows from the v2.1 Kanban.
8 | Technical remediation statuses are unchanged: TEC-09 and TEC-10 remain Review; SUB-02 remains To Do; DEL-05 remains at risk.
STATUS PROGRESS MAPPING |  |  |  | STATUS LEGEND
Done | 100% | Task-level acceptance evidence exists |  | Done | Accepted
Review | 85% | Artifact exists; acceptance or sign-off remains |  | Review | Acceptance open
Doing | 55% | Active critical-path work |  | Doing | Active
To Do | 0% | Defined and ready |  | To Do | Ready
Deferred | 0% | Outside assessed MVP |  | Deferred | No schedule