## Midway Gantt
Blockmediary — Midway Gantt v2
Weekly view ¦ 8 June–14 August 2026 ¦ Status date 28 July 2026 ¦ Mid-delivery snapshot
DONE |  |  | REVIEW |  |  | DOING |  |  | TO DO |  |  | DEFERRED |  | ACTIVE PROGRESS
7 |  |  | 0 |  |  | 12 |  |  | 7 |  |  | 1 |  | 26.92%
Bars show the full planned schedule; statuses reflect 28 July 2026. ◆ Proposal: 8 Jun ◆ Status: 28 Jul ◆ Submission: 14 Aug
[6 empty] | June 2026 |  |  |  | July 2026 |  |  |  | August 2026
Task ID | Task | Ownership | Start | Finish | Status | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10
GOV-01 | Proposal handoff | Tamer (A/R) | 2026-06-08 | 2026-06-08 | Done
GOV-02 | Requirements and governance baseline | Tamer (A); Nick and Dan (R) | 2026-06-09 | 2026-06-21 | Done
GOV-03 | Project coordination through submission | Tamer (A/R); Dan (R) | 2026-06-09 | 2026-08-14 | Doing
STR-01 | Market research | Tamer (A/R); Conrad and Mo (C) | 2026-07-01 | 2026-07-07 | Done
STR-02 | Strategic analysis | Tamer (A/R); all leads (C) | 2026-07-08 | 2026-07-14 | Done
STR-03 | Strategic planning | Tamer (A/R); all leads (C) | 2026-07-15 | 2026-07-21 | Done
STR-04 | Financial and legal coordination and oversight | Tamer (A/R); Conrad and Badhri (C) | 2026-07-01 | 2026-07-31 | Doing
PRD-01 | Product workflow and release rules | Dan (A/R); Nick (R) | 2026-06-09 | 2026-07-10 | Done
PRD-02 | Document rules and pitch alignment | Dan (A); Nick and Badhri (R); Tamer (C) | 2026-06-22 | 2026-08-12 | Doing
TEC-01 | Smart contract and contract tests | Nick (A/R); Dan (R) | 2026-06-15 | 2026-07-10 | Done
TEC-02 | Application lifecycle, authentication and persistence | Nick (A/R); Dan (R) | 2026-06-22 | 2026-08-05 | Doing
TEC-03 | Testnet deployment and onboarding gate | Nick (A); Dan (R) | 2026-06-30 | 2026-08-10 | Doing
TEC-04 | Integrated acceptance and clean-build reproducibility | Nick (A/R); Dan (R) | 2026-08-03 | 2026-08-12 | To Do
UX-01 | Role journeys and consolidated dashboard | Mo (A/R); Nick and Dan (C) | 2026-06-22 | 2026-08-08 | Doing
UX-02 | Canonical demo route and polish | Mo (A/R); Dan (R); Tamer (C) | 2026-08-03 | 2026-08-12 | To Do
UX-03 | Front-end UI implementation | Mo (A/R); Nick and Dan (C); Tamer (I) | 2026-06-22 | 2026-08-08 | Doing
TEC-05 | Back-end application integration | Mo (A/R); Nick and Dan (C); Tamer (I) | 2026-07-15 | 2026-08-10 | Doing
RISK-01 | Legal, regulatory and document research | Badhri (A/R); Tamer (C) | 2026-06-09 | 2026-08-05 | Doing
RISK-02 | Final legal and compliance claim review | Badhri (A/R); Tamer and Nick (C) | 2026-08-03 | 2026-08-12 | To Do
BUS-01 | Financial model, pricing and funding assumptions | Conrad (A/R); Mo (R); Tamer (C) | 2026-06-09 | 2026-08-12 | Doing
BUS-02 | Customer, competitor and market case | Mo (A/R); Tamer, Conrad and Badhri (C) | 2026-06-09 | 2026-08-12 | Doing
BUS-03 | Business model and commercial narrative | Tamer (A/R); Conrad and Badhri (C) | 2026-08-12 | 2026-08-12 | To Do
SUB-01 | Final deck and script | Tamer (A/R); Dan and Mo (R); other leads (C) | 2026-07-27 | 2026-08-12 | Doing
SUB-02 | Demo runbook | Dan (A/R); Nick (R); Mo (C) | 2026-08-03 | 2026-08-12 | To Do
SUB-03 | Rehearsals and recordings | Dan (A/R); Tamer and Mo (R); Nick (C) | 2026-08-10 | 2026-08-13 | To Do
SUB-04 | Submission QA and upload | Tamer (A/R); Dan (R); Mo (C) | 2026-08-13 | 2026-08-14 | To Do
DEF-01 | Post-MVP integrations and production hardening | Tamer (A); technical and domain leads (C) |  |  | Deferred
Note on G8: Proposal handoff — 8 June 2026
Note on P8: Final week ends with submission on 14 August 2026