## Gantt
Blockmediary — Build Gantt Chart (Transakt)
Bar length = task size (Total Effort in team-days). T-shirt sizing per Tony Wood BEEM063 deck (XS=3, S=7, M=12, L=20, XL=30).
ID | Scope | Workstream | Task | Dev | Test | Deploy | Total (days) | Size | 1 |  |  | 6 |  | 11 |  |  | 16 |  | 21 |  | 26 |  | 31 |  | 36 | 41 |  | 46 | 51
1 | MVP | Setup & Infra | Set up monorepo and developer environment (env files / faucets / accounts) | 2 | 0 | 1 |  | XS | XS
2 | MVP | Setup & Infra | Configure deployment pipeline and secrets management | 2 | 1 | 1 |  | S |  | S
3 | MVP | Smart Contract | Implement Escrow smart contract (state machine + role gating) | 6 | 3 | 1 |  | M | M
4 | MVP | Smart Contract | Implement MockUSDC and ERC20 integration | 2 | 1 | 0 |  | XS | [5 empty] | XS
5 | MVP | Smart Contract | Write contract test suite (happy path / access / refund) | 4 | 2 | 0 |  | S | [6 empty] | S
6 | MVP | Smart Contract | Deploy and verify contract on Base Sepolia (Ignition) | 2 | 1 | 2 |  | S | [9 empty] | S
7 | MVP | Frontend | Scaffold Next.js app and wallet connect (wagmi / RainbowKit) | 4 | 1 | 1 |  | S | S
8 | MVP | Frontend | Build buyer panel (approve / deposit / balance) | 5 | 2 | 1 |  | M |  |  |  |  | M
9 | MVP | Frontend | Build seller panel (upload / verdict / release) | 5 | 2 | 1 |  | M | [7 empty] | M
10 | MVP | Frontend | Implement on-chain event watching and state sync | 3 | 2 | 1 |  | S | [11 empty] | S
11 | MVP | Doc Verification | Build document upload API endpoint | 3 | 1 | 1 |  | S | S
12 | MVP | Doc Verification | Integrate Claude vision extraction with Zod schema | 5 | 3 | 1 |  | M |  |  |  | M
13 | MVP | Doc Verification | Implement deterministic rules engine | 4 | 3 | 1 |  | M | [7 empty] | M
14 | MVP | Doc Verification | Build authorised releaser bridge (recordVerdict on-chain) | 3 | 2 | 1 |  | S | [11 empty] | S
15 | MVP | Doc Verification | Implement audit-ledger logging | 2 | 1 | 1 |  | S | [13 empty] | S
16 | MVP | Deal Intake | Build escrow-spec intake form (structured terms to JSON) | 5 | 2 | 1 |  | M | M
17 | MVP | Demo & Deliverables | Write demo runbook and seed script | 2 | 1 | 1 |  | S | S
18 | MVP | Demo & Deliverables | Record fallback demo video | 2 | 1 | 0 |  | XS |  |  | XS
19 | Roadmap | Compliance | Build KYC / sanctions screening stub | 6 | 3 | 1 |  | M | [15 empty] | M
20 | Roadmap | Dispute | Build dispute objection window and worker | 8 | 4 | 2 |  | L | [15 empty] | L
21 | Roadmap | Smart Contract | Extend to full state-machine coverage (v2 contract) | 7 | 4 | 2 |  | L | [15 empty] | L
22 | Roadmap | Frontend | Build buyer/seller multi-deal dashboard | 8 | 3 | 1 |  | M | [15 empty] | M
23 | Roadmap | Frontend | Build audit-ledger viewer UI | 4 | 2 | 1 |  | S | [18 empty] | S
24 | Roadmap | Orchestration | Build multi-agent orchestrator (Agent SDK) | 10 | 5 | 2 |  | L | [15 empty] | L
MVP SUBTOTAL
ROADMAP SUBTOTAL
GRAND TOTAL

## Legend
Legend & Method
Workstream colours
Setup & Infra
Smart Contract
Frontend
Doc Verification
Deal Intake
Demo & Deliverables
Compliance
Dispute
Orchestration
T-shirt sizing (Total Effort → days)
XS | up to 3 days
S | 4–7 days
M | 8–12 days
L | 13–20 days
XL | 21–30 days
XXL | 30+ days
Method
• Each bar's length = the task's Total Effort (Dev+Test+Deploy) in team-days, straight from sizing.csv.
• Tasks are sequenced serially within each workstream; separate workstreams run in parallel.
• MVP block runs first; the Roadmap block begins after the longest MVP workstream finishes.
• Day numbers across the top are cumulative team-days, not calendar dates (the team parallelises work).
• Source: proposal/sizing.csv. Totals are live formulas (=Dev+Test+Deploy).